## Risks and Opportunities
Risks | Consequence | Probability | Damage | Expected Damage
No internal resources available. | Risk does not materialize. | 60% | 0 | 16000
| Hire externally 1 staff. | 20% | 10000
| Hire externally 5 staff. | 10% | 50000
| Hire externally 9 staff. | 10% | 90000
Design does not fulfil specification. | Risk does not materialize. | 40% | 0 | 800000
| Partial redesign of unit. | 40% | 1000000
| Complete redesign of unit. | 20% | 2000000
Cost target cannot be achieved. | Risk does not materialize. | 50% | 0 | 210000
| Redesign component #1. | 10% | 200000
| Redesign component #1, #2. | 10% | 300000
| Redesign component #1, #2, #3. | 20% | 400000
| Redesign component #1, #2, #3, #4. | 10% | 800000
1026000
Opportunities | Consequence | Probability | Benefit | Expected Benefit
Win a prize in the "engineer of the year" competition. | Opportunity does not materialize. | 80% | 0 | 5500
| Win 2nd prize. | 15% | 20000
| Win 1st prize. | 5% | 50000
International commercialization starts ahead of planning. | Opportunity does not materialize. | 70% | 0 | 350000
| Launch ahead of plan in major EU markets. | 20% | 1000000
| Launch ahead of plan in all EU markets. | 10% | 1500000
355500

## Output
Risk and Opportunity Outcomes
Value | Probability | Distribution | 1-Distribution
-1550000 | 0.0006 | 0.0006 | 0.9994
-1540000 | 0.0002 | 0.0008 | 0.9992
-1520000 | 0.0018 | 0.0026 | 0.9974
-1510000 | 0.0006 | 0.0032 | 0.9968
-1500000 | 0.0097 | 0.0129 | 0.9871
-1490000 | 0.0032 | 0.0161 | 0.9839
-1470000 | 0.0003 | 0.0164 | 0.9836
-1460000 | 0.0001 | 0.0165 | 0.9835
-1450000 | 0.0016 | 0.0181 | 0.9819
-1430000 | 0.0003 | 0.0184 | 0.9816
-1410000 | 0.0016 | 0.02 | 0.98
-1350000 | 0.00012 | 0.02012 | 0.97988
-1340000 | 4e-05 | 0.02016 | 0.97984
-1320000 | 0.00036 | 0.02052 | 0.97948
-1310000 | 0.00012 | 0.02064 | 0.97936
-1300000 | 0.00194 | 0.02258 | 0.97742
-1290000 | 0.00064 | 0.02322 | 0.97678
-1270000 | 6e-05 | 0.02328 | 0.97672
-1260000 | 2e-05 | 0.0233 | 0.9767
-1250000 | 0.00044 | 0.02374 | 0.97626
-1240000 | 4e-05 | 0.02378 | 0.97622
-1230000 | 6e-05 | 0.02384 | 0.97616
-1220000 | 0.00036 | 0.0242 | 0.9758
-1210000 | 0.00044 | 0.02464 | 0.97536
-1200000 | 0.00194 | 0.02658 | 0.97342
-1190000 | 0.00064 | 0.02722 | 0.97278
-1170000 | 6e-05 | 0.02728 | 0.97272
-1160000 | 2e-05 | 0.0273 | 0.9727
-1150000 | 0.00056 | 0.02786 | 0.97214
-1140000 | 8e-05 | 0.02794 | 0.97206
-1130000 | 6e-05 | 0.028 | 0.972
-1120000 | 0.00072 | 0.02872 | 0.97128
-1110000 | 0.00056 | 0.02928 | 0.97072
-1100000 | 0.00388 | 0.03316 | 0.96684
-1090000 | 0.00128 | 0.03444 | 0.96556
-1070000 | 0.00012 | 0.03456 | 0.96544
-1060000 | 4e-05 | 0.0346 | 0.9654
-1050000 | 0.00184 | 0.03644 | 0.96356
-1040000 | 0.0004 | 0.03684 | 0.96316
-1030000 | 0.00012 | 0.03696 | 0.96304
-1020000 | 0.0036 | 0.04056 | 0.95944
-1010000 | 0.00184 | 0.0424 | 0.9576
-1000000 | 0.0194 | 0.0618 | 0.9382
-990000 | 0.0064 | 0.0682 | 0.9318
-970000 | 0.0006 | 0.0688 | 0.9312
-960000 | 0.0002 | 0.069 | 0.931
-950000 | 0.0032 | 0.0722 | 0.9278
-930000 | 0.0006 | 0.0728 | 0.9272
-910000 | 0.0032 | 0.076 | 0.924
-850000 | 0.00024 | 0.07624 | 0.92376
-840000 | 8e-05 | 0.07632 | 0.92368
-820000 | 0.00072 | 0.07704 | 0.92296
-810000 | 0.00024 | 0.07728 | 0.92272
-800000 | 0.00388 | 0.08116 | 0.91884
-790000 | 0.00128 | 0.08244 | 0.91756
-770000 | 0.00012 | 0.08256 | 0.91744
-760000 | 4e-05 | 0.0826 | 0.9174
-750000 | 0.001 | 0.0836 | 0.9164
-740000 | 0.00012 | 0.08372 | 0.91628
-730000 | 0.00012 | 0.08384 | 0.91616
-720000 | 0.00108 | 0.08492 | 0.91508
-710000 | 0.001 | 0.08592 | 0.91408
-700000 | 0.00582 | 0.09174 | 0.90826
-690000 | 0.00192 | 0.09366 | 0.90634
-670000 | 0.00018 | 0.09384 | 0.90616
-660000 | 6e-05 | 0.0939 | 0.9061
-650000 | 0.00144 | 0.09534 | 0.90466
-640000 | 0.00016 | 0.0955 | 0.9045
-630000 | 0.00018 | 0.09568 | 0.90432
-620000 | 0.00144 | 0.09712 | 0.90288
-610000 | 0.00144 | 0.09856 | 0.90144
-600000 | 0.00776 | 0.10632 | 0.89368
-590000 | 0.00256 | 0.10888 | 0.89112
-570000 | 0.00024 | 0.10912 | 0.89088
-560000 | 8e-05 | 0.1092 | 0.8908
-550000 | 0.00188 | 0.11108 | 0.88892
-540000 | 0.0002 | 0.11128 | 0.88872
-530000 | 0.00024 | 0.11152 | 0.88848
-520000 | 0.0018 | 0.11332 | 0.88668
-510000 | 0.00188 | 0.1152 | 0.8848
-500000 | 0.0097 | 0.1249 | 0.8751
-490000 | 0.0032 | 0.1281 | 0.8719
-470000 | 0.0003 | 0.1284 | 0.8716
-460000 | 0.0001 | 0.1285 | 0.8715
-450000 | 0.0016 | 0.1301 | 0.8699
-430000 | 0.0003 | 0.1304 | 0.8696
-410000 | 0.0016 | 0.132 | 0.868
-350000 | 0.00012 | 0.13212 | 0.86788
-340000 | 4e-05 | 0.13216 | 0.86784
-320000 | 0.00036 | 0.13252 | 0.86748
-310000 | 0.00012 | 0.13264 | 0.86736
-300000 | 0.00194 | 0.13458 | 0.86542
-290000 | 0.00064 | 0.13522 | 0.86478
-270000 | 6e-05 | 0.13528 | 0.86472
-260000 | 2e-05 | 0.1353 | 0.8647
-250000 | 0.00068 | 0.13598 | 0.86402
-240000 | 0.00012 | 0.1361 | 0.8639
-230000 | 6e-05 | 0.13616 | 0.86384
-220000 | 0.00108 | 0.13724 | 0.86276
-210000 | 0.00068 | 0.13792 | 0.86208
-200000 | 0.00582 | 0.14374 | 0.85626
-190000 | 0.00192 | 0.14566 | 0.85434
-170000 | 0.00018 | 0.14584 | 0.85416
-160000 | 6e-05 | 0.1459 | 0.8541
-150000 | 0.0012 | 0.1471 | 0.8529
-140000 | 8e-05 | 0.14718 | 0.85282
-130000 | 0.00018 | 0.14736 | 0.85264
-120000 | 0.00072 | 0.14808 | 0.85192
-110000 | 0.0012 | 0.14928 | 0.85072
-100000 | 0.00388 | 0.15316 | 0.84684
-90000 | 0.00128 | 0.15444 | 0.84556
-70000 | 0.00012 | 0.15456 | 0.84544
-60000 | 4e-05 | 0.1546 | 0.8454
-50000 | 0.00604 | 0.16064 | 0.83936
-40000 | 0.0018 | 0.16244 | 0.83756
-30000 | 0.00012 | 0.16256 | 0.83744
-20000 | 0.0162 | 0.17876 | 0.82124
-10000 | 0.00604 | 0.1848 | 0.8152
0 | 0.0873 | 0.2721 | 0.7279
10000 | 0.0288 | 0.3009 | 0.6991
30000 | 0.0027 | 0.3036 | 0.6964
40000 | 0.0009 | 0.3045 | 0.6955
50000 | 0.0144 | 0.3189 | 0.6811
70000 | 0.0027 | 0.3216 | 0.6784
90000 | 0.0144 | 0.336 | 0.664
150000 | 0.00108 | 0.33708 | 0.66292
160000 | 0.00036 | 0.33744 | 0.66256
180000 | 0.00324 | 0.34068 | 0.65932
190000 | 0.00108 | 0.34176 | 0.65824
200000 | 0.01746 | 0.35922 | 0.64078
210000 | 0.00576 | 0.36498 | 0.63502
230000 | 0.00054 | 0.36552 | 0.63448
240000 | 0.00018 | 0.3657 | 0.6343
250000 | 0.00408 | 0.36978 | 0.63022
260000 | 0.0004 | 0.37018 | 0.62982
270000 | 0.00054 | 0.37072 | 0.62928
280000 | 0.0036 | 0.37432 | 0.62568
290000 | 0.00408 | 0.3784 | 0.6216
300000 | 0.0194 | 0.3978 | 0.6022
310000 | 0.0064 | 0.4042 | 0.5958
330000 | 0.0006 | 0.4048 | 0.5952
340000 | 0.0002 | 0.405 | 0.595
350000 | 0.00536 | 0.41036 | 0.58964
360000 | 0.00072 | 0.41108 | 0.58892
370000 | 0.0006 | 0.41168 | 0.58832
380000 | 0.00648 | 0.41816 | 0.58184
390000 | 0.00536 | 0.42352 | 0.57648
400000 | 0.03492 | 0.45844 | 0.54156
410000 | 0.01152 | 0.46996 | 0.53004
430000 | 0.00108 | 0.47104 | 0.52896
440000 | 0.00036 | 0.4714 | 0.5286
450000 | 0.00606 | 0.47746 | 0.52254
460000 | 0.0001 | 0.47756 | 0.52244
470000 | 0.00108 | 0.47864 | 0.52136
480000 | 0.0009 | 0.47954 | 0.52046
490000 | 0.00606 | 0.4856 | 0.5144
500000 | 0.00485 | 0.49045 | 0.50955
510000 | 0.0016 | 0.49205 | 0.50795
530000 | 0.00015 | 0.4922 | 0.5078
540000 | 5e-05 | 0.49225 | 0.50775
550000 | 0.0008 | 0.49305 | 0.50695
570000 | 0.00015 | 0.4932 | 0.5068
590000 | 0.0008 | 0.494 | 0.506
650000 | 6e-05 | 0.49406 | 0.50594
660000 | 2e-05 | 0.49408 | 0.50592
680000 | 0.00018 | 0.49426 | 0.50574
690000 | 6e-05 | 0.49432 | 0.50568
700000 | 0.00097 | 0.49529 | 0.50471
710000 | 0.00032 | 0.49561 | 0.50439
730000 | 3e-05 | 0.49564 | 0.50436
740000 | 1e-05 | 0.49565 | 0.50435
750000 | 0.0013 | 0.49695 | 0.50305
760000 | 0.00038 | 0.49733 | 0.50267
770000 | 3e-05 | 0.49736 | 0.50264
780000 | 0.00342 | 0.50078 | 0.49922
790000 | 0.0013 | 0.50208 | 0.49792
800000 | 0.01843 | 0.52051 | 0.47949
810000 | 0.00608 | 0.52659 | 0.47341
830000 | 0.00057 | 0.52716 | 0.47284
840000 | 0.00019 | 0.52735 | 0.47265
850000 | 0.00316 | 0.53051 | 0.46949
860000 | 4e-05 | 0.53055 | 0.46945
870000 | 0.00057 | 0.53112 | 0.46888
880000 | 0.00036 | 0.53148 | 0.46852
890000 | 0.00316 | 0.53464 | 0.46536
900000 | 0.00194 | 0.53658 | 0.46342
910000 | 0.00064 | 0.53722 | 0.46278
930000 | 6e-05 | 0.53728 | 0.46272
940000 | 2e-05 | 0.5373 | 0.4627
950000 | 0.00512 | 0.54242 | 0.45758
960000 | 0.0016 | 0.54402 | 0.45598
970000 | 6e-05 | 0.54408 | 0.45592
980000 | 0.0144 | 0.55848 | 0.44152
990000 | 0.00512 | 0.5636 | 0.4364
1000000 | 0.0776 | 0.6412 | 0.3588
1010000 | 0.0256 | 0.6668 | 0.3332
1030000 | 0.0024 | 0.6692 | 0.3308
1040000 | 0.0008 | 0.67 | 0.33
1050000 | 0.0128 | 0.6828 | 0.3172
1070000 | 0.0024 | 0.6852 | 0.3148
1090000 | 0.0128 | 0.698 | 0.302
1150000 | 0.00096 | 0.69896 | 0.30104
1160000 | 0.00032 | 0.69928 | 0.30072
1180000 | 0.00288 | 0.70216 | 0.29784
1190000 | 0.00096 | 0.70312 | 0.29688
1200000 | 0.01552 | 0.71864 | 0.28136
1210000 | 0.00512 | 0.72376 | 0.27624
1230000 | 0.00048 | 0.72424 | 0.27576
1240000 | 0.00016 | 0.7244 | 0.2756
1250000 | 0.00358 | 0.72798 | 0.27202
1260000 | 0.00034 | 0.72832 | 0.27168
1270000 | 0.00048 | 0.7288 | 0.2712
1280000 | 0.00306 | 0.73186 | 0.26814
1290000 | 0.00358 | 0.73544 | 0.26456
1300000 | 0.01649 | 0.75193 | 0.24807
1310000 | 0.00544 | 0.75737 | 0.24263
1330000 | 0.00051 | 0.75788 | 0.24212
1340000 | 0.00017 | 0.75805 | 0.24195
1350000 | 0.00464 | 0.76269 | 0.23731
1360000 | 0.00064 | 0.76333 | 0.23667
1370000 | 0.00051 | 0.76384 | 0.23616
1380000 | 0.00576 | 0.7696 | 0.2304
1390000 | 0.00464 | 0.77424 | 0.22576
1400000 | 0.03104 | 0.80528 | 0.19472
1410000 | 0.01024 | 0.81552 | 0.18448
1430000 | 0.00096 | 0.81648 | 0.18352
1440000 | 0.00032 | 0.8168 | 0.1832
1450000 | 0.00512 | 0.82192 | 0.17808
1470000 | 0.00096 | 0.82288 | 0.17712
1490000 | 0.00512 | 0.828 | 0.172
1750000 | 0.00096 | 0.82896 | 0.17104
1760000 | 0.00032 | 0.82928 | 0.17072
1780000 | 0.00288 | 0.83216 | 0.16784
1790000 | 0.00096 | 0.83312 | 0.16688
1800000 | 0.01552 | 0.84864 | 0.15136
1810000 | 0.00512 | 0.85376 | 0.14624
1830000 | 0.00048 | 0.85424 | 0.14576
1840000 | 0.00016 | 0.8544 | 0.1456
1850000 | 0.00256 | 0.85696 | 0.14304
1870000 | 0.00048 | 0.85744 | 0.14256
1890000 | 0.00256 | 0.86 | 0.14
1950000 | 0.0021 | 0.8621 | 0.1379
1960000 | 0.0007 | 0.8628 | 0.1372
1980000 | 0.0063 | 0.8691 | 0.1309
1990000 | 0.0021 | 0.8712 | 0.1288
2000000 | 0.03395 | 0.90515 | 0.09485
2010000 | 0.0112 | 0.91635 | 0.08365
2030000 | 0.00105 | 0.9174 | 0.0826
2040000 | 0.00035 | 0.91775 | 0.08225
2050000 | 0.0056 | 0.92335 | 0.07665
2070000 | 0.00105 | 0.9244 | 0.0756
2090000 | 0.0056 | 0.93 | 0.07
2150000 | 0.00042 | 0.93042 | 0.06958
2160000 | 0.00014 | 0.93056 | 0.06944
2180000 | 0.00126 | 0.93182 | 0.06818
2190000 | 0.00042 | 0.93224 | 0.06776
2200000 | 0.00679 | 0.93903 | 0.06097
2210000 | 0.00224 | 0.94127 | 0.05873
2230000 | 0.00021 | 0.94148 | 0.05852
2240000 | 7e-05 | 0.94155 | 0.05845
2250000 | 0.00154 | 0.94309 | 0.05691
2260000 | 0.00014 | 0.94323 | 0.05677
2270000 | 0.00021 | 0.94344 | 0.05656
2280000 | 0.00126 | 0.9447 | 0.0553
2290000 | 0.00154 | 0.94624 | 0.05376
2300000 | 0.00679 | 0.95303 | 0.04697
2310000 | 0.00224 | 0.95527 | 0.04473
2330000 | 0.00021 | 0.95548 | 0.04452
2340000 | 7e-05 | 0.95555 | 0.04445
2350000 | 0.00196 | 0.95751 | 0.04249
2360000 | 0.00028 | 0.95779 | 0.04221
2370000 | 0.00021 | 0.958 | 0.042
2380000 | 0.00252 | 0.96052 | 0.03948
2390000 | 0.00196 | 0.96248 | 0.03752
2400000 | 0.01358 | 0.97606 | 0.02394
2410000 | 0.00448 | 0.98054 | 0.01946
2430000 | 0.00042 | 0.98096 | 0.01904
2440000 | 0.00014 | 0.9811 | 0.0189
2450000 | 0.00224 | 0.98334 | 0.01666
2470000 | 0.00042 | 0.98376 | 0.01624
2490000 | 0.00224 | 0.986 | 0.014
2750000 | 0.00042 | 0.98642 | 0.01358
2760000 | 0.00014 | 0.98656 | 0.01344
2780000 | 0.00126 | 0.98782 | 0.01218
2790000 | 0.00042 | 0.98824 | 0.01176
2800000 | 0.00679 | 0.99503 | 0.0049699
2810000 | 0.00224 | 0.99727 | 0.0027299
2830000 | 0.00021 | 0.99748 | 0.0025199
2840000 | 7e-05 | 0.99755 | 0.0024499
2850000 | 0.00112 | 0.99867 | 0.0013299
2870000 | 0.00021 | 0.99888 | 0.0011199
2890000 | 0.00112 | 1 | -6.333e-08

## Commands and Scripts
bash
cat risks_opportunities_input.dat ¦ ./faltung4.exe > risks_opportunities_output.dat
head -n297 risks_opportunities_output.dat > risks_opportunities_density.dat
tail -n293 risks_opportunities_output.dat > risks_opportunities_distribution.dat
gnuplot for the example in the text
# Opportunity and Risk (Probability Curve)
set term qt size 1000, 800
set xrange[-1600:+2900]
set yrange[0.0:+1.0]
set ytics 0.1
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Combined Opportunity and Risk Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability of a cumulated value > x" offset -0.1,0 font "Verdana,14"
plot "risks_opportunities_distribution.dat" using (($1)/1000):(1-($2)) linewidth 1 pointtype 8
# Opportunity and Risk (Probability Density)
set term qt size 1000, 800
set xrange[-1600:+2900]
set yrange[0.0:+0.1]
set ytics 0.01
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability density of the combined opportunity and risk value " offset -0.5,0 font "Verdana,14"
plot "risks_opportunities_density.dat" using (($1)/1000):2 linewidth 1 pointtype 8
gnuplot for the binary distribution of equal risks and opportunities with 50%
# Opportunity and Risk (Probability Curve)
set term png size 1000, 800
set output 'risks_opportunities_distribution_2_50.png'
set xrange[-200:+200]
set yrange[0.0:+1.0]
set ytics 0.1
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Combined Opportunity and Risk Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability of a cumulated value > x" offset -0.1,0 font "Verdana,14"
plot "risks_opportunities_distribution_2_50.dat" using (($1)/1000):(1-($2)) linewidth 1 pointtype 8
# Opportunity and Risk (Probability Density)
set term png size 1000, 800
set output 'risks_opportunities_density_2_50.png'
set xrange[-200:+200]
set yrange[0.0:+0.045]
set ytics 0.005
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability density of the combined opportunity and risk value " offset -0.5,0 font "Verdana,14"
plot "risks_opportunities_density_2_50.dat" using (($1)/1000):2 linewidth 1 pointtype 8
gnuplot for the binary distribution of risks only with 50%
# Opportunity and Risk (Probability Curve)
set term png size 1000, 800
set output 'risks_distribution_2_50.png'
set xrange[0:+200]
set yrange[0.0:+1.0]
set ytics 0.1
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Risk Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability of a cumulated value > x" offset -0.1,0 font "Verdana,14"
plot "risks_distribution_2_50.dat" using (($1)/1000):(1-($2)) linewidth 1 pointtype 8
# Opportunity and Risk (Probability Density)
set term png size 1000, 800
set output 'risks_density_2_50.png'
set xrange[0:+200]
set yrange[0.0:+0.06]
set ytics 0.01
set grid xtics lt 0 lw 2
set grid ytics lt 0 lw 2
set xtics font "Verdana,14"
set ytics font "Verdana,14"
set xlabel "Risk Value in $ 1000 " offset 0,-0.1 font "Verdana,14"
set ylabel "Probability density of the risk value " offset -0.5,0 font "Verdana,14"
plot "risks_density_2_50.dat" using (($1)/1000):2 linewidth 1 pointtype 8